## Overall
S19 Report File Reference | Date of Incident | Investigation Status | Overall Works Status | Risk Management Authorities with Responsibilities and whether they are exercising | LCC / Disctrict Council Work Status | EA Work Status | IDB Work Status | National Highway Work Status | Water Company Work Status | Description of Flooding | Reccomendations for Consideration
S19 - 1019 | 2025-09-04 | Completed | On-Going | Lincolnshire County Council - Yes // Anglian Water - TBC | On-Going | N/A | N/A | N/A | TBC | Based on the available evidence, it is considered that the mechanism of flooding was attributed to the local public and private surface water drainage systems being overwhelmed and having their capacity exceeded following a localised very high intensity, short duration rainfall event. Whilst rainfall events of this nature have the potential to highlight defects within systems, even those that are functioning at their original design standard were not, generally speaking, designed to mitigate the magnitude of surface water generated in such a short timeframe.This resulted in exceedance of the network and accumulation of surface water at the lowest sections in the affected areas. | Task 1 - Anglian Water to consider investigating/CCTV surveying the public surface water sewer in the affected areas from the junction with Highfield Road and along High Street to the system’s outfall, with cleansing and any remedial action undertaken if necessary to ensure the system is functioning to its original design standard.
S19 - 965 | 2025-01-06 | Completed | On-Going | Lincolnshire County Council - Yes // Anglian Water - TBC // Upper Witham Internal Drainage Board - TBC | On-Going | N/A | Completed | N/A | On-Going | The predominant flood mechanism was attributed to prolonged rainfall increasing the levels within the Foss Dyke Navigation, leading to an exceedance of the surface water drainage network along Sykes Lane from backing up into the system. This consequently led to surface water flows accumulating on the highway, surcharging the private and public foul sewers, and surface water network. The flood mechanism for the affected area by Lincoln Road was ascribed to the highway surface water drainage system backing up once high levels were reached in the Foss Dyke, leading to surface water accumulation on the road, as well as adjacent ordinary watercourses overtopping due to being unable to discharge excess surface water flows. | Task 2 - Lincolnshire County Council (LCC) as Highways Authority to consider completing the works to investigate the highway drainage assets in the affected area and cleanse to outfall where possible. Subject to findings, further investigation or improvement works should be undertaken if required to ensure highways assets are functioning to the original design standard. Task 2 update (28/5/26) - The system has been jetted and cleansed.
S19 - 687 | 2023-10-20 | Completed | On-Going | Lincolnshire County Council - Yes // Anglian Water -TBC // Upper Witham Internal Drainage Board - Yes | On-Going | N/A | Completed | N/A | On-Going | The flood mechanisms at the affected properties were attributed to a combination of factors including: surface water runoff from the highway from capacity exceedance and / or surcharging of local surface water and foul sewer systems, due to antecedent saturated catchment conditions and high rainfall, as well as surface water flows from the overtopping of field ditches and local ordinary watercourses. In some areas, this issue was compounded by local systems being unable to effectively discharge into the Foss Dyke due to elevated levels in the watercourse, which further contributed to generation of surface water flows towards the affected properties. | Task 3 - The implementation of property flood resilience (PFR) measures should be considered by owners/managers of the affected properties, as advised by LCC as Lead Local Flood Authority where necessary.
S19 - 900 | 2023-10-20 | Completed | On-Going | Lincolnshire County Council - Yes // Anglian Water - TBC // Upper Witham Internal Drainage Board - Yes | On-Going | N/A | Completed | N/A | On-Going | The flood mechanisms to the affected properties were attributed to a combination of factors including: surface water runoff from the highway from capacity exceedance and / or surcharging of local surface water and foul sewer systems, due to antecedent saturated catchment conditions and high rainfall, as well as surface water flows from the overtopping of field ditches and local ordinary watercourses. In some areas, this issue was compounded by local systems being unable to effectively discharge into the Foss Dyke due to elevated levels in the watercourse, which further contributed to generation of surface water flows towards the affected properties. | Task 3 - The relevant RMAs concerned review, and where possible, implement the recommendations proposed in S19-687 which are also relevant to this investigation. Please refer updates from the previous investigation.
S19 - 1031 | 2026-02-28 | TBC | TBC | TBC | TBC | TBC | TBC | N/A | TBC | This investigation is on-going and will be updated upon its completion | The investigation is ongoing and these records shall be updated on its completion.

## Overview
S19 Report File Reference | Date of Incident | Investigation Status | Overall Works Status | Risk Management Authorities with Responsibilities and whether they are exercising
S19 - 1019 | 2025-09-04 | Completed | On-Going | Lincolnshire County Council - Yes // Anglian Water - TBC
S19 - 965 | 2025-01-06 | Completed | On-Going | Lincolnshire County Council - Yes // Anglian Water - TBC // Upper Witham Internal Drainage Board - TBC
S19 - 687 | 2023-10-20 | Completed | On-Going | Lincolnshire County Council - Yes // Anglian Water -TBC // Upper Witham Internal Drainage Board - Yes
S19 - 900 | 2023-10-20 | Completed | On-Going | Lincolnshire County Council - Yes // Anglian Water - TBC // Upper Witham Internal Drainage Board - Yes
S19 - 1031 | 2026-02-28 | TBC | TBC | TBC

## Description and Reccomendations
S19 Report File Reference | Description of Flooding | Reccomendations for Consideration
S19 - 1019 | Based on the available evidence, it is considered that the mechanism of flooding was attributed to the local public and private surface water drainage systems being overwhelmed and having their capacity exceeded following a localised very high intensity, short duration rainfall event. Whilst rainfall events of this nature have the potential to highlight defects within systems, even those that are functioning at their original design standard were not, generally speaking, designed to mitigate the magnitude of surface water generated in such a short timeframe.This resulted in exceedance of the network and accumulation of surface water at the lowest sections in the affected areas. | Task 1 - Anglian Water to consider investigating/CCTV surveying the public surface water sewer in the affected areas from the junction with Highfield Road and along High Street to the system’s outfall, with cleansing and any remedial action undertaken if necessary to ensure the system is functioning to its original design standard. Task 2 - Lincolnshire County Council (LCC) as Highways Authority to consider completing the works to investigate the highway drainage assets in the affected area and cleanse to outfall where possible. Subject to findings, further investigation or improvement works should be undertaken if required to ensure highways assets are functioning to the original design standard. Task 2 update (28/5/26) - The system has been jetted and cleansed. Task 3 - The implementation of property flood resilience (PFR) measures should be considered by owners/managers of the affected properties, as advised by LCC as Lead Local Flood Authority where necessary.
S19 - 965 | The predominant flood mechanism was attributed to prolonged rainfall increasing the levels within the Foss Dyke Navigation, leading to an exceedance of the surface water drainage network along Sykes Lane from backing up into the system. This consequently led to surface water flows accumulating on the highway, surcharging the private and public foul sewers, and surface water network. The flood mechanism for the affected area by Lincoln Road was ascribed to the highway surface water drainage system backing up once high levels were reached in the Foss Dyke, leading to surface water accumulation on the road, as well as adjacent ordinary watercourses overtopping due to being unable to discharge excess surface water flows. | Task 1 - Anglian Water to consider investigating the public foul sewer network at the affected areas of Lincoln Road and Sykes Lane, and the surface water sewer network along Sykes Lane, to confirm there are no defects or misconnections present, and that the capacity of the networks is sufficient. Subject to the findings, the installation of non-return valves (NRVs) in the foul sewer network connections could be considered, if deemed as appropriate, to minimise the opportunity for excess water surcharging at the properties. Task 2 - Lincolnshire County Council (LCC) as Lead Local Flood Authority (LLFA) considers advising affected residents of Property Flood Resilience (PFR) measures which could be implemented, where not already done so, as well as having regard to advising on potential funding options for such measures where available. Task 2 update (19/11/2025) - Information on Property Flood Resilience (PFR) measures sent to affected properties via the LCC administered scheme. Task 3 - The relevant RMAs concerned review, and where possible, implement the recommendations proposed in S19-687 which are also relevant to this investigation. Please refer updates from the previous investigation. Task 4 - LCC as Highways Authority consider investigating the highway drainage gullies along the full length of Sykes Lane, to ascertain any potential connections to additional systems and / or blockages. If any blockages or defects are noted within the assets, the necessary reparations should be considered. Consideration should be given to the implementation of non-return valves (NRVs) at the outfall of highway drainage into the Foss Dyke along Lincoln Road, if deemed as appropriate, to minimise the opportunity of backflow into the system. Task 5 - LCC as LLFA, alongside Upper Witham Internal Drainage Board (UWIDB) where necessary, to consider identifying and working with relevant landowners to advise on riparian ownership and maintenance responsibilities for the ordinary watercourses to the west of the affected area on Lincoln Road, as well as exploring what, if any, potential opportunities exist to reduce the risk of overland flows from higher elevation land. Task 5 update (13/10/2025) - UWIDB updated "The Board will continue to remind riparian owners of their responsibilities if any enquiries arise or if necessary within enforcement cases, consent applications or planning matters." Task 6 - West Lindsey District Council considers assessing the PFR measures implemented at properties on Sykes Lane and their effectiveness, with remedial measures undertaken if deemed as necessary.
S19 - 687 | The flood mechanisms at the affected properties were attributed to a combination of factors including: surface water runoff from the highway from capacity exceedance and / or surcharging of local surface water and foul sewer systems, due to antecedent saturated catchment conditions and high rainfall, as well as surface water flows from the overtopping of field ditches and local ordinary watercourses. In some areas, this issue was compounded by local systems being unable to effectively discharge into the Foss Dyke due to elevated levels in the watercourse, which further contributed to generation of surface water flows towards the affected properties. | Task 1 - Lincolnshire County Council (LCC) as Lead Local Flood Authority (LLFA) in collaboration with other relevant RMAs should consider investigating the feasibility of localised flood alleviation schemes in or around the affected areas in Saxilby, subject to funding and other potential limitations. Task 2 - LCC as Highways Authority should consider carrying out any outstanding repairs/improvements to the surface water drainage system on Sykes Lane as outlined in the 2022 CCTV survey, where deemed as necessary. Further CCTV surveying may be required to determine the extent of repairs which may be required on Sykes Lane. Task 2 update (14/01/2025) - Revisit completed on 12/06/2024 from previous works, civils works carried out and system confirmed as running. Task 3 - LCC as Highways Authority to consider reviewing the kerb heights adjacent to the properties specifically referenced in the report, and consider carrying out any remedial works deemed as necessary. Task 4 - LCC as Highways Authority should consider reviewing the road drainage systems and road grading on Mill Lane, to ensure that the drainage is operating satisfactorily, with appropriate investigation into any remedial/upgrade works where deemed as necessary. Task 5 - LCC as Highways Authority should consider reviewing the highway drainage arrangement along West Bank alongside the condition of the carriageway, to confirm whether further works are required to resurface in areas where seepage of water from the Foss Dyke may be possible, to maximise the mitigation of excess surface water flows when river levels are high. Task 5 update (26/01/2026) - A drainage works scheme is being progressed by LCC Highways, alongside relevant Risk Management Authorities. Task 6 - Anglian Water should consider investigating the foul sewer system along West Bank and Sykes Lane, and the surface water system which serves Sykes Lane in the areas adjacent to the affected properties. Any investigation should consider whether there are any local defects, with the results informing whether any necessary remedial action to the systems is undertaken. Task 7 - LCC as LLFA and Upper Witham Internal Drainage Board should consider reviewing the capacity and condition of drainage ditches around the referenced areas in Saxilby, and ensure riparian landowners are advised on maintenance responsibilities, where necessary. Maintenance and improvement works should be carried out, where issues are identified, by the relevant riparian owners. Task 7 update (08/07/2025) - LCC and Upper Witham Internal Drainage Board (UWIDB)carried out inspection of referenced ordinary watercourses adjacent to Sykes Lane. UWIDB to engage with relevant landowners to advise on riparian maintenance responsiblities due to the condition of some systems following visit. Task 7 update (22/07/2025) - UWIDB in correspondence with landowners regarding maintenance of ditches to the north of the northern affected properties on Sykes Lane, who have confirmed that riparian maintenance is to be carried out on the ditches in this area. Task 7 update (22/10/2025) - Flailing and vegetation maintenance has been carried out where possible by riparian owners as advised by UWIDB. Task 8 - LCC as LLFA should consider ensuring that the residents have access to appropriate flood risk guidance, outlining actions that should be taken when there is flood alert or flood warning issued by the Environment Agency, as well as consider advising those affected of the national Property Flood Resilience guidance that was published in 2021. Task 8 update (08/01/2026) - Following Storm Babet and the announcement of the Government Property Flood Resilience (PFR) Grant (via Defra and administered by LCC) all property owners impacted by internal flooding to the living space were provided with the opportunity to apply for grant money to support the installation of PFR measures. Those who have taken the opportunity are being supported through the LCC Floods and Water Team with surveys and installation through appointed contractors. Task 9 - In its Emergency Planning role, LCC should consider engagement with the local Parish Council and community in establishing Flood Action Groups and/or developing Flood Plans if they are not already established and developed. Task 9 update (26/01/2026) - The Lincolnshire Resilience Forum (LRF) through the Resilient Communities Programme, are working with communities and parishes across the county to develop Flood Action Groups and Plans, alongside information on preparedness through the Community Resilience Newsletter and LRF website.
S19 - 900 | The flood mechanisms to the affected properties were attributed to a combination of factors including: surface water runoff from the highway from capacity exceedance and / or surcharging of local surface water and foul sewer systems, due to antecedent saturated catchment conditions and high rainfall, as well as surface water flows from the overtopping of field ditches and local ordinary watercourses. In some areas, this issue was compounded by local systems being unable to effectively discharge into the Foss Dyke due to elevated levels in the watercourse, which further contributed to generation of surface water flows towards the affected properties. | Task 1 - Lincolnshire County Council (LCC) as Lead Local Flood Authority (LLFA) in collaboration with other relevant RMAs should consider investigating the feasibility of localised flood alleviation schemes in or around the affected areas in Saxilby, subject to funding and other potential limitations. Task 2 - LCC as Highways Authority should consider carrying out any outstanding repairs/improvements to the surface water drainage system on Sykes Lane as outlined in the 2022 CCTV survey, where deemed as necessary. Further CCTV surveying may be required to determine the extent of repairs which may be required on Sykes Lane. Task 2 update (14/01/2025) - Revisit completed on 12/06/2024 from previous works, civils works carried out and system confirmed as running. Task 3 - LCC as Highways Authority to consider reviewing the kerb heights adjacent to the properties specifically referenced in the report, and consider carrying out any remedial works deemed as necessary. Task 4 - LCC as Highways Authority should consider reviewing the road drainage systems and road grading on Mill Lane, to ensure that the drainage is operating satisfactorily, with appropriate investigation into any remedial/upgrade works where deemed as necessary. Task 5 - LCC as Highways Authority should consider reviewing the highway drainage arrangement along West Bank alongside the condition of the carriageway, to confirm whether further works are required to resurface in areas where seepage of water from the Foss Dyke may be possible, to maximise the mitigation of excess surface water flows when river levels are high. Task 5 update (26/01/2026) - A drainage works scheme is being progressed by LCC Highways, alongside relevant Risk Management Authorities. Task 6 - Anglian Water should consider investigating the foul sewer system along West Bank and Sykes Lane, and the surface water system which serves Sykes Lane in the areas adjacent to the affected properties. Any investigation should consider whether there are any local defects, with the results informing whether any necessary remedial action to the systems is undertaken. Task 7 - LCC as LLFA and Upper Witham Internal Drainage Board should consider reviewing the capacity and condition of drainage ditches around the referenced areas in Saxilby, and ensure riparian landowners are advised on maintenance responsibilities, where necessary. Maintenance and improvement works should be carried out, where issues are identified, by the relevant riparian owners. Task 7 update (08/07/2025) - LCC and Upper Witham Internal Drainage Board (UWIDB)carried out inspection of referenced ordinary watercourses adjacent to Sykes Lane. UWIDB to engage with relevant landowners to advise on riparian maintenance responsiblities due to the condition of some systems following visit. Task 7 update (22/07/2025) - UWIDB in correspondence with landowners regarding maintenance of ditches to the north of the northern affected properties on Sykes Lane, who have confirmed that riparian maintenance is to be carried out on the ditches in this area. Task 7 update (22/10/2025) - Flailing and vegetation maintenance has been carried out where possible by riparian owners as advised by UWIDB. Task 8 - LCC as LLFA should consider ensuring that the residents have access to appropriate flood risk guidance, outlining actions that should be taken when there is flood alert or flood warning issued by the Environment Agency, as well as consider advising those affected of the national Property Flood Resilience guidance that was published in 2021. Task 8 update (08/01/2026) - Following Storm Babet and the announcement of the Government Property Flood Resilience (PFR) Grant (via Defra and administered by LCC) all property owners impacted by internal flooding to the living space were provided with the opportunity to apply for grant money to support the installation of PFR measures. Those who have taken the opportunity are being supported through the LCC Floods and Water Team with surveys and installation through appointed contractors. Task 9 - In its Emergency Planning role, LCC should consider engagement with the local Parish Council and community in establishing Flood Action Groups and/or developing Flood Plans if they are not already established and developed. Task 9 update (26/01/2026) - The Lincolnshire Resilience Forum (LRF) through the Resilient Communities Programme, are working with communities and parishes across the county to develop Flood Action Groups and Plans, alongside information on preparedness through the Community Resilience Newsletter and LRF website.
S19 - 1031 | This investigation is on-going and will be updated upon its completion | This investigation is on-going and will be updated upon its completion

## Reccomendation by Organisation
S19 Report File Reference | LCC / Disctrict Council Work Status | EA Work Status | IDB Work Status | National Highway Work Status | Water Company Work Status
S19 - 1019 | On-Going | N/A | N/A | N/A | TBC
S19 - 965 | On-Going | N/A | Completed | N/A | On-Going
S19 - 687 | On-Going | N/A | Completed | N/A | On-Going
S19 - 900 | On-Going | N/A | Completed | N/A | On-Going
S19 - 1031 | TBC | TBC | TBC | N/A | TBC